## Feasibility Study
League Fixture Generator System — Feasibility Study
Menoufia University — Faculty of Computers and Information ¦ System Analysis & Design Project (Second Year, 2026–2027)
Note: All figures, operational scenarios, and schedule estimates below are proposed student-project assumptions to be validated with stakeholder interviews.
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Fixtures are prepared manually on paper or in spreadsheets. Pairing teams round-by-round and checking venue/date availability by hand causes team double-bookings, venue clashes, and manual rework after any match postponement. | Web-based application built with standard coursework tools (HTML, CSS, JavaScript frontend; server-side backend; relational database) using a round-robin pairing algorithm (with automatic bye handling for odd team counts and conflict-free date/venue assignment). | Technically Feasible
Operational | Manual tournament coordination takes several hours per draft, is prone to overlapping pitch bookings, struggles to balance home/away matches and rest days, and distributes schedules late in inconsistent formats (screenshots or paper copies). | Automated single/double round-robin fixture generation (knockout optional), fast regeneration of affected rounds after changes, simple organizer interface, view-only team access, printable PDF/spreadsheet export, and basic match result & standings tracking. | Operationally Feasible
Economic | Manual scheduling wastes organizer hours each semester and causes administrative errors, while commercial league management software licenses are unnecessarily expensive for an amateur or university sports committee. | Developed in-house by the 5-student team using free open-source tools ($0 software license cost). Illustrative first-year setup and hosting costs ($150–$400, midpoint $275) are outweighed by estimated annual time/admin savings ($630–$970, midpoint $800), with payback in ~4.1 months. | Cost-Effective
Legal | Requires compliance with basic participant data privacy, university/amateur sports committee regulations, fair-play scheduling rules, and software licensing terms. | Stores only essential league data (team names, venues, match times, scores), enforces role-based access (organizer edit vs. team view-only), applies transparent scheduling constraints, and uses free open-source technologies with no proprietary license issues. | Legally Feasible
Schedule | Manual scheduling delays tournament planning and league kickoff dates. The proposed system itself must be completed within the academic project schedule. | Planned across 60 working days (~12 weeks) using the Waterfall SDLC: Planning (9 days, 15%), Analysis (12 days, 20%), Design (21 days, 35%), and Implementation (18 days, 30%), matching the PERT critical path and Gantt schedule. | Achievable Timeline
SDLC Schedule Feasibility & Time Estimation Alignment (60 Working Days Total)
SDLC Phase | Main Activities & PERT Tasks | Standard SDLC Share | Estimated Duration (Days)
Planning | Tasks T1–T3 (Days 1–9): System Request & Project Identification (T1, 3d), Feasibility Study (T2, 3d), Methodology, PERT & Gantt (T3, 3d) | 15% | 9
Analysis | Tasks T4–T10 (Days 10–21): Interview (T4, 4d), Questionnaire (T5, 3d), DFDs (T6, 3d), Data Store (T7, 2d), Process Spec. (T8, 2d), ERD (T9, 3d), Normalization (T10, 2d) | 20% | 12
Design | Task T11 (Days 22–42): System Design — Architecture, Relational Database Schema, Physical DFD/ERD & UI Prototype (21d) | 35% | 21
Implementation | Task T12 (Days 43–60): Implementation, Round-Robin Fixture Generation Engine, Data Entry, Export & System Testing (18d) | 30% | 18
Total | Critical Path: T1 → T2 → T3 → T4 → T6 → T7/T8 → T9 → T11 → T12 (60 Working Days) | 100% | 60

## Cost-Benefit Analysis
Cost-Benefit Analysis — League Fixture Generator System
Student-Project Economic Feasibility Model (Illustrative First-Year Estimates in USD — Adapted for an Amateur / University League Scenario)
Assumption Note: All dollar amounts are illustrative student-project estimates (assuming free open-source development tools, basic cloud/local hosting, and valued organizer hours saved across two semesters/year).
Category | Description (Cost Scope) | Est. Cost Low ($) | Est. Cost High ($) | Est. Cost Midpoint ($) | Benefits & Operational Impact | Annual Value Low ($) | Annual Value High ($) | Annual Value Midpoint ($)
Software | In-house development by the 5-student team using free open-source tools ($0 license cost; optional domain/SSL & dev utilities) | 0 | 100 | 50 | Centralized, automated round-robin fixture generator eliminates scheduling clashes and manual pairing errors | 200 | 300 | 250
Hardware | Basic shared cloud web hosting, database storage, and automated backups (or local university server deployment) | 60 | 120 | 90 | Faster schedule generation; 24/7 browser access and reduced manual venue/date coordination time | 150 | 250 | 200
Training | Short walkthrough session (1–2 hours) and concise user guide for the league organizer and fixture planner | 20 | 40 | 30 | Smooth transition from spreadsheets and faster onboarding of student organizers each semester | 80 | 120 | 100
Maintenance | Routine semester updates, minor bug fixes, and database backup checks across the academic year | 40 | 80 | 60 | Ensures system reliability, conflict prevention, and fast schedule regeneration after match postponements | 120 | 180 | 150
Administration | Transition from paper calendars, printed drafts, and manual spreadsheets to a single digital workflow | 30 | 60 | 45 | Eliminates manual paper sheets and version confusion via consistent PDF and spreadsheet exports | 80 | 120 | 100
User Experience | Manual fixture preparation previously caused late schedules, consecutive-day fatigue, and fairness complaints ($0 extra fee) | 0 | 0 | 0 | Intangible qualitative benefit: balanced home/away matches, fair rest days, and higher team satisfaction ($0 direct cash assumed) | 0 | 0 | 0
Total | Total Estimated First-Year Costs (Range: $150 – $400; Midpoint: $275) | 150 | 400 | 275 | Total Estimated Annual Benefits / Savings (Range: $630 – $970; Midpoint: $800) | 630 | 970 | 800
Economic Feasibility Summary & Payback Analysis
Net Annual Benefit ($) | Annual Benefits minus First-Year Costs (Low / High / Expected Midpoint) | 480 | 570 | 525 | Positive net benefit across all scenarios ($480 to $570; expected $525 in Year 1; conservative bound Low Benefit $630 − High Cost $400 = +$230).
Payback Period (Years) | First-Year Costs divided by Annual Benefits (Low Cost / High Cost / Midpoint) | 0.2381 | 0.41237 | 0.34375 | Payback achieved within ~0.24 to 0.41 years (expected 0.34 years, or ~4.1 months); even worst-case High Cost / Low Benefit ($400 / $630) pays back in 0.63 years (~7.6 months, well within 1 year).
Payback Period (Months) | Estimated months to recover initial setup and hosting costs | 2.8571 | 4.9485 | 4.125 | Expected payback within the first academic semester (~4.1 months).
First-Year ROI (%) | Net First-Year Benefit divided by First-Year Cost | 320% | 142.5% | 190.9% | Strong return on investment (expected 190.9% in Year 1) driven by zero software licensing cost and automated schedule generation.
Conclusion: The League Fixture Generator System is economically feasible for a student/university project, recovering its illustrative first-year setup and hosting costs ($150–$400) within 1 year (~4.1 months expected) while eliminating scheduling conflicts and reducing manual organizer workload.